# Plan and timeline

Project: GenAI in Receivables Management

1. Objective To deliver a strategic presentation to Accenture demonstrating how specific AI Agents transform standard L4/L5 Receivables Management processes, shifting them from "Human-Driven" to "AI-Driven" workflows.

2. Team Structure (9 Members) Organized into 3 streams, each led by a Graduate Student.

| Team/Members | Focus Area | Assigned Agents | L5 Process Owner |
| --- | --- | --- | --- |
| Team A - Saandiya (grad) - Tolu (Grad) - Parth (undergrad) | AR Ledger | • Accounts Receivable Agent • Accounts Receivable | • Lockbox • Cash & Checks • ACH/Wire |
| Team B - Byron - Rhea - Mayank | Disputes | • Dispute Resolution Agent • Agent for Missing Credits • Contract Accounting | • Dispute Case Opening • Dispute Case Management |
| Team C - Allison Neff (undergrad) - Tanvi (Grad) - Prabhu (Grad) | Risk & Revenue | • Behavioral Insights • Agent for Incorrect Credits | • Bad Debt Reserves • KPI Reporting • Revenue Assurance |

3. Execution Strategy: The "Overlay" Method For every assigned process, teams must answer six core questions to map the "To-Be" state :

- Definition: What does the agent do?

- Work: What specific task does it perform?

- Placement: Where does it fit in the L5 flow steps?

- Process Change: How does the flow logic/path change?

- Persona Impact: How does the human role change?

- Automation Level: Is the step now Manual, Human-Assisted, or AI-Driven? .

4. Timeline

- Week 1-2: Discovery & As-Is Mapping (Week of 12/15, 12/22)

  - Activity: Teams review assigned L5 docs and map current "pain points" (e.g., manual matching).

  - Deliverable: Annotated "Current State" process flows.

- Week 3-4: Solution Design (To-Be)  (Week of 12/29, 1/5)

  - Activity: Overlay AI Agents onto the flows using the 6-point strategy. Create "Persona Impact" slides.

  - Deliverable: Draft "Future State" slides and modified process maps.

- Week 5: Consolidation & Value (Week of 1/12)

  - Activity: Graduate Leads merge the three decks. Teams quantify value (e.g., efficiency gains, error reduction).

  - Deliverable: Unified Master Deck v1.

- Week 5: First Draft Presentation (Week of 1/12)

  - Activity: Refine narrative, check against Accenture requirements, and rehearse.

  - Deliverable: First Draft Presentation for Accenture.

1/12 - out of country

Jan 5 - Presentation Draft ready

Jan 12 - Presentation Final

Jan 14 - Accenture Meeting (6 pm London Time)

# Questions for 12/12

Waiting to get back for:

- L5 processes for Revenue Assurance Control Management

- Contract Accounting -Dispute Resolution Agent for Incorrect credits not present in SAP website

From meeting:

- Good time to present first draft the week of 12th january is Wednesday 14th 6pm London time.

# Kick-off meeting

## Oct 30, 2025 | Accenture Kick-Off Meeting

Attendees:

Notes

- Ralph lauren - global transformation of their organization

- Sell their products through e-commerce, wholesale, stores

- They have applications and technologies, SAP (enterprise resource planning solution), software that runs large organizations, supply chains, etc

- They have legacies around the world that is used for retail, move the product

- Looking to standardise, drive standard business process, technology across business

- To reduce cost, enable artificial intelligence

- Getting inventory correct, efficient inventory planning

- Program is a 3-4 year timeline, they started in June

- Goes through implementation in europe, north america, asia pacific, rest of the world

- Drive standardization to be efficient - inventory, visibility to inventory, 3 areas

- AI team - within SAP - building AI solutions within the software

- Predelivered solutions from SAP - cash application - time consuming, manually intensive

- Get in and understand what are the impacts, what data, business process, is it actually improving throughput, is it working or not, what's the impact on the organization

- What does that look like from a people perspective

- Concepts of agentic AI - supervisor agent, tax agent - how to piece those agents together to become more efficient

- Think how people work with these machines, how does a person have a coworker that is AI

- Kishore, ken will help us out

- Budget is multi hundred million dollars/billion dollars

- People comes from different areas - ralph lauren, accenture, SAP

- Biswa - overall program manager lead, how to track these informations

- Deliverables and outcomes, track things like risks and issues

- Real life issue - client is struggling with a big decision in inventory - what should i do or not do?

- Test what types of gen AI applications can we apply to the information biswa has to help predict the future

- When are pieces going to fall together, what areas should i be concerned about

- Figure out how to take all these informations and use it to help the leaders to predict what will happen in the future

- Sample real project plans, past data - how we can use that

- Team 2 - kishore

Action items

- Student leads - 2 for AI team

- Set weekly internal meeting times

- Set weekly professor meeting time

- Set initial Accenture meeting with lead

- Split group into 2?

# Questions from team

Questions to clients

- Behind the scenes and more information on SAP cash application.

- When coming up with a solution, are we thinking of a specific region like the US? Because Ralph Lauren is large, and different regions move differently.

- Specific use case areas

- What are the specific deliverables in Phase 1?

# Notes 12/5

- Standardise business practices

- Optimize SAP software

- Have SAP solutions function better, more efficiently, take decision

Test cases on how to do this and how to make it work

Can an agent actually do those steps, which steps, what are the impacts to the people

What will change in the process

What will i need to do to activate the agent

How will the process flow change

What is the dispute agent doing

How are all the agents working together

8 agents - process flows, figure out what you think will change between the process within this agents

Important to capture what its not doing as well

Demo to show it into an environment

Look at use cases, variations

Prereq, dependencies - data, software that we need to use these agents

Specific region cases

Benefits, provable, values - x minutes saved … - tie it out, does it actually benefit the role/system

# Team A

Roles:
1. Process, data, and human role placement - Parth

- Flow, input/output, how the human fits around the agent. prereq/dependencies,

2. Decision & Automation Logic - Saandiya

- auto/manual, decision flow, who decides what

3. Risk, Failure & Controls - Tolu

- Edge cases, what could go wrong, what can break and how to fix

| Overlay Question | Role |
| --- | --- |
| What does the agent do? | Role 1 |
| What task does it perform? | Role 1 |
| Where does it fit in L5? | Role 1 |
| How does the flow change? | Role 1 |
| When is it automated? | Role 2 |
| When does it escalate? | Role 2 |
| How does the human role change? | Role 1 + 3 |
| What are the risks? | Role 3 |